|  | FM701-10A DCC Category 2 PRE CONSTRUCTION INFORMATION & CONSTRUCTION PHASE PLAN |  |
| --- | --- | --- |
| 1.0 PRE CONSTRUCTION INFORMATION (to be completed by client) |  |  |
| 1.1 Project details: R6016 – Clepington Road |  |  |
| Name & address of client: Dundee City Council, Executive Director of City Development Client Officer: Ewan MacNaughton Division: Sustainable Transport and Roads Telephone: 01382 434000 email: ewan.macnaughton@dundeecity.gov.uk |  | Designer (if not client): Jake McAllister on behalf of Head of Sustainable Transport and Roads Telephone: 01382 834028 email: jake.mcallister@dundeecity.gov.uk CDM Principal Designer (if required): NA |
| Client ref or Work/GVA order: |  | Project Number: R6016 |
| Contractor/Principal Contractor: Tayside Contracts Address: Contracts House, 1 Soutar Street, DD3 8SS Contact: TBC Telephone: 01382 812721 email: TBC |  |  |
| Project Address: Clepington Road between the Tak A Wa (Chinese takeaway) and 187 Clepington Road Description of Work Carriageway works: (Carriageway Resurfacing: As per R6016-DCC-ZZ-DR-C-001&002 Resurfacing Plan & Cross section drawings) 40mm Carriageway Resurfacing – 805m² - Plane off the existing carriageway surface to a depth of 40mm across the full extents. A Dundee City Council Engineer will be present during operations to identify any localised areas requiring deeper excavation up to 100mm. Post milling: - Regulate as required using Hot Rolled Asphalt (HRA) 30/14F surface regulating course (40/60 pen), applied in accordance with the stated conversion factor (0.43 m³/t). - Lay 40mm HRA 30/14F (40/60 pen) Surface Course. Execution requirements: - Ensure pre-coated chippings are evenly distributed and fully embedded in accordance with specification. - Record and verify material temperatures on delivery and immediately prior to laying to confirm compliance with HRA laying temperature requirements. - Form smooth transition ramps at tie-in points to accommodate live traffic where required. - Maintain traffic flow between 15:30 and 07:30, ensuring safe and practical temporary running surfaces at all times. 100mm Carriageway Resurfacing – 1565m² Plane off the existing carriageway surface to an initial depth of 40mm, with further excavation to 100mm total depth where instructed on site. Construction build-up to comprise: - Regulating layer using HRA 30/14F (40/60 pen) where required to achieve correct levels and profile. - Binder course: 60mm HRA 50/20 (40/60 pen). - Surface course: 40mm HRA 30/14F (40/60 pen). Execution requirements: - Ensure all materials are laid within specified minimum and maximum temperature tolerances, with checks undertaken at delivery and point of lay. - Achieve full compaction and bond between layers, with no segregation or surface defects. - Apply pre-coated chippings uniformly to the surface course. - Maintain appropriate traffic management and safe transitions during restricted working hours. During the day a temporary road surface should be available for the public to use as the road will return to normal use between 3.30pm – 7am Ironwork: (R6016-DCC-ZZ-DR-C-003). 12 no. Scottish water Manhole cover and frame to be reset. 1 no. Gas cover to be replaced. 5 no. existing gully gratings to be adjusted and tied into new surface levels Lining works: All road markings to be installed as per the specifications provided in the lining diagrams referenced in the Master Lining Plan (R6016-DCC-ZZ-DR-C-004). |  |  |
| Proposed Timescales: Start - 20/04/2026 |  | Finish – 01/05/2026 |
| Occupier/tenant/owner on-site and their contact details: As part of the Pre-Construction Information (PCI) process, Dundee City Council has been notified of the proposed works. All residents and businesses along Clepington road have been contacted in advance of the commencement of construction activities to ensure proper communication and mitigate any potential disruptions. Attention has been given to North End Motors, they are aware that the road will be completely shut with no access, however if there is the opportunity to leave an access open for them then this would be preferable |  |  |
| Arrangements for security of the site: Heras fencing to be erected around the perimeter of the site to segregate members of the public from the working area and prevent unauthorised access. Ensure all excavations are covered or made safe at all times. The neighbouring footpaths will be open to members of the public for the duration of the works. Out of hours contact details: Tayside Contracts emergency contact - 07767326827 |  |  |
| Onsite Welfare Facilities : Toilet: Yes/No Washing Facilities (hot and cold water): Yes/No Rest Facilities: Yes/No Mains Drinking Water: Yes/No Heated Changing Room: Yes/No |  |  |

| - Project specific hazards - Client to highlight site hazards and provide details under headings. Note that this is not an exhaustive list Refer to R6016-DCC-ZZ-DR-C-001 for site specific hazards - Where appropriate, Client to provide existing Health & Safety File | Contractors RAMS reference |
| --- | --- |
| Working at height N/A |  |
| Slips trips & falls No unusual slip or trip hazards. Contractor to ensure site is tidy at all times |  |
| Excavations and services - Utilities are present, plans in site file, however the accuracy of the plans is unreliable and therefore the designs and construction should eliminate the potential impact with utilities by not exceeding 300mm deep - excavation depth to be minimised where practicable; trial holes and CAT scanning to be undertaken due to uncertain utility records - All excavations must be made safe when left unattended. |  |
| Collapse of structures/materials - N/A |  |
| Health Hazards - The Construction Phase Plan to include risk assessments, method statements and procedures to protect all personnel working or attending site. |  |
| Exposure to asbestos N/A |  |
| Risks to members of the public, building users and others: Here’s a concise version of the information you provided, formatted for inclusion in a notice or communication: Traffic Management and Safety Measures These works will take place under a road closure and will be protected in accordance with the Safety at Street Works and Road Works Code of Practice (CoP). Key details of the traffic management plan include: - The works will be conducted under a road closure on Clepington Road, between the Tak A Wa Chinese takeaway on Clepington Road to approx. the eastbound bus stop prior to Graham Street. The have all been informed that no access will be permitted between 7am and 3.30pm. - The works will be carried out in two phase of working. Once the roundabout is resurfaced, it should be opened for 24 hour public use as usual. - Pedestrian access for businesses and residents will be maintained at all times. - Vehicular access for emergency services will be maintained throughout the duration of the works. |  |
| Environmental policies All waste generated through cold milling to be removed from site |  |
| Other dangers on site that would not be readily known by contractor, eg The contractor must adhere with latest government guidance relating to dealing with COVID-19 pandemic |  |
| - Additional information provided by client: eg other activities in the area which may affect the construction phase In the area surrounding the planned resurfacing works, there may be other activities or factors that could affect the construction phase. These include: - Businesses in the area: Contact has been made by the client with each business, each business has been informed of no possible access between 7.30am and 3.30pm throughout the duration of the works |  |

2.0 CONSTRUCTION PHASE PLAN (To be completed and returned by Contractor/Principal Contractor)

2.1 Control measures for issues identified by Client in 1.2 & 1.3 above be required to inform the residents of the scope of the works and times that they have to vacate the street. Info boards will be set out 7 days prior to start. 1. All waste material will be removed to the appropriate disposal site. 2. The works will be carried out under a full road closure to ensure the safety of the work force and members of the public. 3. To minimise inconvenience the surfacing works will be carried out under 2 phases. 4. The site has evidence of heave caused by tree routes, advice to be sought prior to works commencing. 5. A letter drop from the client will be required to inform the residents of the scope of the works and times that they have to vacate the street. Info boards will be set out 7 days prior to start.

2.2 Updates to Construction Phase Plan: - Updates will be agreed with the client and approved in writing prior to implementation. The onsite information can be amended or updated via a mobile network and device. The CCP will be updated in writing and saved on the M, drive the onsite copy will receive amendments via a mobile device. All verbal instructions will also be confirmed in writing and the onsite folder updated to reflect any changes.

2.3 Communications: Communication will be both verbal and written. Changes to design or specification will be confirmed in writing once necessary Risk assessments have been conducted and a safe method of work agreed. The site chargehand will be in possession of a mobile device to review site files and drawings also the facility to attend MS Teams meetings if the project engineer or client are unable to attend in person.

2.4 Details of key members of Project Team Client /Designer – Jake McAllister Project Engineer – Garry Robertson Chargehand – Rory Keen Chargehand – Out of hours contact details: See Developed safety information.

2.5 Site rules See RAMS

We acknowledge receipt of the Pre Construction Information and have detailed above our control measures for the Construction Phase Plan. Signed TO BE COMPLETED BY CONTRACTOR Print name GARRY ROBERTSON Date: 03/04/26 Proposed date for commencement of works: 18/04/26

Construction Phase Plan considered sufficiently developed to allow works to commence on site Signed TO BE COMPLETED BY CLIENT Print name JAKE MCALLISTER Date: 19.03.26

3.0 Post Contract

(To be completed and returned by Contractor/Principal Contractor)

We confirm that the following documents have been submitted to the client (tick as appropriate):

- Updated Health and Safety File

- Asbestos Management Survey records

- Fire stopping records

- Local Authority completion certificate

- Log of accidents, incidents, RIDDOR incidents

- Compliance certification

- Other, give details

Signed…………………………………………………………..(Contractor)

Print name ……………………………………………………..Date:……………………………………

The works were completed and signed off on:…………………………………………………………

| Rev | Date | Description | Prepared | Reviewed | Approved |
| --- | --- | --- | --- | --- | --- |
| A | 1st June 2020 | COVID 19 provisions added | Stewart Cheyne | Andrew Lorimer | Neil Martin |